## GCP Cost Estimation
16500
PROTON CRM — Monthly Recurring (one production tenant)
| No | GCP Component | Component Details | Price (USD) | Price (IDR)
| 1 | Google Kubernetes Engine (Standard) — cluster | Region: Singapore (asia-southeast1) Regional cluster management fee ($0.10/cluster/hr) Multi-tenant: per-tenant namespaces + node pools | 73
| 2 | Google Kubernetes Engine (Standard) — node pool | 3 × e2-standard-4 (vCPUs: 4, RAM: 16 GiB), on-demand Runs Chatwoot (Rails+Sidekiq), agent & backend (FastAPI) | 362.01
| 3 | Cloud SQL for PostgreSQL (HA) | Region: Singapore (asia-southeast1) Enterprise edition, regional HA Machine: 2 vCPU / 8 GiB RAM Storage: 100 GB SSD Chatwoot DB + per-tenant pgvector KB | 300
| 4 | Memorystore for Redis (HA) | Standard tier (auto-failover replica) Capacity: 4 GB Sidekiq queues / cache | 181.04
| 5 | Vertex AI — Gemini 2.5 Flash + Vertex AI Search | Usage-based (indicative) ~5,000 AI conversations/mo (~8k in + ~1.5k out tokens) ~5,000 grounded KB queries/mo | 50.75
| 6 | Cloud Storage | Region: Singapore (asia-southeast1) Class: Standard · 100 GB + modest egress Attachments / exports | 8.3
| 7 | Networking — Cloud Load Balancing + egress | 1 external HTTP(S) forwarding rule + data processing ~100 GB internet egress/mo | 31.85
| 8 | Cloud Logging + Cloud Monitoring | ~100 GB log ingest/mo (first 50 GB free) Metrics + alerting | 25
| 9 | Secret Manager + Artifact Registry + Cloud Build + BigQuery | Secrets · container images · CI builds · analytics warehouse (storage + query) | 17.25
Total Price Estimation Per-Month
Total Price Estimation Per-Year
Calculator Link: https://cloud.google.com/products/calculator
One-time — Migration Period *
| No | GCP Component | Component Details | Price (USD) | Price (IDR)
| 1 | Cloud Storage — migration staging | Zendesk export staging bucket (Standard, ~50 GB, short-lived) | 5
| 2 | Data transfer / egress — migration | One-time import/export bandwidth for tickets, contacts, KB, attachments | 15
| 3 | Temporary migration compute | Short-lived job for bulk import + KB ingest into Vertex AI Search / pgvector | 20
Total Price Estimation Per-Month
Total Price Estimation Per-Year
Calculator Link: https://cloud.google.com/products/calculator
*one time only during migration process
IDR shown at USD→IDR = cell A1 (16,500, editable). Indicative GCP list price (Jul 2026, asia-southeast1 / Singapore — nearest full-service region; Malaysia region not yet GA). Excludes negotiated discounts, taxes & Google program funding. 1-yr committed-use discount lowers nodes ~$233 → ~$920/mo total.

## Timeline
Phases |  | Task | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16
Assessment & Planning
1.0 | 1.1 | Kick-off, scope & SOP validation; confirm requirements from BRD + Process-Flow workbook
| 1.2 | Solution architecture, migration plan & GCP landing zone design (GKE Standard, VPC, IAM)
GCP Foundation & Provisioning
2.0 | 2.1 | Provision GCP project, VPC, GKE Standard cluster + node pools, Cloud SQL, Memorystore, BigQuery
| 2.2 | CI/CD (Artifact Registry + Cloud Build), Secret Manager, monitoring baseline
Core Platform Cutover
3.0 | 3.1 | Deploy Chatwoot + agent + backend on GKE Standard + Cloud SQL
| 3.2 | Zendesk data migration (tickets, contacts, KB, attachments) + parallel-run
| 3.3 | Wire channels: WhatsApp (Twilio), Website, API; KB migration to Vertex AI Search
| 3.4 | AI layer + SOP lifecycle flows (disclaimer, idle-close, YES/NO, rating, auto-classify)
Gap Closure (P2 priorities)
4.0 | 4.1 | Email escalation — auto-ack once/thread + separate internal case (SOP-driven)
| 4.2 | Customer 360 + DMS/TSP integration (4-section card, <3s sync)
| 4.3 | Case management — hierarchical categories, per-ticket dashboard, RBAC
| 4.4 | Reporting & BI — BigQuery + Power BI, role-based views, anomaly dashboard, NPS/CRR
| 4.5 | Agent management (channel priority, auto-busy) + multimodal / language + bulk KB upload
Hardening, UAT & Handover
5.0 | 5.1 | HA / autoscaling, monitoring & alerting, backups / DR
| 5.2 | UAT, data reconciliation & sign-off
| 5.3 | Cut-over, Zendesk decommission, ops runbook + admin/agent training

## PS Utilization
16500
[14 empty] | Role / Seniority | Sales price / hour (IDR) | Per day (× 8)
| Professional Services — PROTON CRM (self-managed on Google Cloud) | [5 empty] | Lead Consultant | Principal | Senior Consultant | Consultant | Senior Consultant | Consultant | Total | Consultant | 350000
| Milestone | Activity | Resources | Duration (Week) | Service Price | Duration (Days) | Project Manager | Solution Architect / Tech Lead | Backend / AI Engineer | Frontend Engineer | Data / BI Engineer | QA Engineer | (mandays) | Senior Consultant | 606250
| Phase 1 : Assessment & Planning | Kick-off, scope & SOP validation; confirm requirements from BRD + Process-Flow workbook; solution architecture & migration plan. | Project Manager Solution Architect Backend/AI Engineer Data/BI Engineer | 2 |  |  | 3 | 6 | 4 | 0 | 2 | 1 |  | Lead Consultant | 700000
| Phase 2 : GCP Foundation & Provisioning | Provision GCP project, VPC, GKE Standard cluster + node pools, Cloud SQL, Memorystore, BigQuery; CI/CD, Secret Manager, monitoring baseline. | Solution Architect DevOps / Backend Data/BI Engineer | 2 |  |  | 3 | 6 | 8 | 1 | 2 | 1 |  | Principal | 825000
| Phase 3 : Core Platform Cutover | Deploy Chatwoot + agent + backend on GKE Standard + Cloud SQL; Zendesk data migration + parallel-run; wire WhatsApp/Web/API; KB migration; AI + SOP lifecycle flows. | Project Manager Backend/AI Engineer Frontend Engineer Data/BI Engineer QA | 4 |  |  | 5 | 5 | 26 | 8 | 6 | 6 |  | Expert / Director | 1275000
| Phase 4 : Gap Closure (P2 priorities) | Email escalation; Customer 360 + DMS/TSP; case management + hierarchical categories + RBAC; reporting & Power BI; agent management + multimodal / language + bulk KB upload. | Backend/AI Engineer Frontend Engineer Data/BI Engineer QA | 6 |  |  | 6 | 5 | 40 | 20 | 16 | 12 |  | Margin | 15%
| Phase 5 : Hardening, HA & UAT | HA / autoscaling, monitoring & alerting, backups / DR; UAT, data reconciliation & sign-off. | DevOps / Backend QA Project Manager | 2 |  |  | 4 | 2 | 12 | 4 | 2 | 12
| Phase 6 : Cutover, Handover & Training | Cut-over, Zendesk decommission; ops runbook + admin/agent training + knowledge transfer. | Project Manager Backend/AI Engineer Technical Writer | 2 |  |  | 3 | 2 | 10 | 3 | 2 | 4
Total Mandays
Total Mandays Price
Total Price Including Margin
Mandays are an indicative delivery estimate; day-rates & margin are editable in the rate card (Q:S). Rp figures use the rates above; USD equivalent at A1 rate. May be offset by Google program funding.