## Slide 1
Self-Managed CRM on Google Cloud
Technical Proposal for PROTON · Replacing Zendesk · v1.0 · 2026-07-27

## Slide 2: Executive Summary
Situation: PROTON's complaint operation runs on Zendesk — a per-seat SaaS CRM. Cost scales with every agent and premium feature; data and AI behaviour sit with the vendor.
Proposal: replace it with a self-managed CRM — Chatwoot Community (no seat licence) + a Google Gemini / Vertex AI layer — on GCP, built to PROTON's own 5-channel SOP.
Why now:
  Cost — eliminate recurring per-agent licensing; pay for infrastructure, not seats.
  Ownership — your conversations, KB, AI prompts and data inside PROTON's GCP tenancy.
  Speed — the majority is already built and demonstrated live against your SOP.
  AI-native — Gemini answers in the customer's language, grounded on your own FAQ/KB.

## Slide 3: Our Understanding of Your Requirements
# | Requirement cluster | What you need
1 | Omnichannel inbound | Call / Email / WhatsApp / Social in one view, single record, alerts, call voice-to-text
2 | Agent management | On-duty check, per-agent channel priorities, status-aware assignment, reminders
3 | FAQ + AI support | Live-editable KB, AI suggested replies from FAQ, one-click refer, quality scoring
4 | Escalation & SLA | Category->PIC routing, email + WhatsApp alerts, case states, 8h/48h auto-escalation
5 | Customer 360 | Two-way DMS + TSP integration, auto-identify by number, 360 view card
6 | Reporting / BI | Channel & dept KPIs, NPS, lifecycle, scheduled PDF/Excel, anomaly alerts, Power BI
Mapped line-by-line from your Customer Complaint Management BR + the 5-channel CRM Process Flow workbook.

## Slide 4: What to Expect
Business Expectation | Technical Expectation
No per-agent / per-seat licence fees | Chatwoot Community (open-source), self-hosted on GCP — unlimited agents
Your data stays yours | All conversations, KB and AI prompts inside PROTON's GCP project
AI answers instantly, in the customer's language | Gemini on Vertex AI, same-language replies, grounded on your FAQ/KB
Your SOP, not a generic product | Disclaimers, idle-close, YES/NO resolution, rating surveys — as code
Faster complaint resolution | Auto-classification -> PIC routing, SLA timers (2-min WA ack ... 48h alarm)
Management visibility | BigQuery analytics + Looker/Power BI, scheduled PDF/Excel, anomaly alerts
Predictable, scalable cost | Managed GCP services; pay for what you consume, scale per tenant
Low delivery risk | Majority already built & demoed live — engagement is migration + hardening

## Slide 5
SECTION 2
Target Architecture
Migrating from Zendesk (SaaS) to a self-managed platform on Google Cloud.

## Slide 6: Current State vs. Target State
TODAY — ZENDESK (SaaS)
• Per-agent subscription; SLA / roles / AI behind paid tiers
• Data and AI behaviour hosted by the vendor
• FAQ / KB inside Zendesk; limited AI-grounding control
• Integrations bolted onto a closed platform
TARGET — SELF-MANAGED ON GCP
• Open-source core; SLA / roles / AI built by us, not rented
• Runs inside PROTON's GCP project — full data control
• KB + AI prompts owned & edited by PROTON (no-code)
• First-party integration surfaces: DMS/TSP, telephony, BI

## Slide 7: GCP Production Architecture
• Presentation: Cloud LB + Caddy (TLS, per-tenant routing)
• Channels: WhatsApp · Email · Social · Web · Voice
• App (managed containers):
– Chatwoot (Rails+Sidekiq) — CRM core
– agent + backend (FastAPI) on GKE / Cloud Run
• AI & knowledge:
– Vertex AI — Gemini (reply, classify)
– Vertex AI Search + pgvector — KB grounding
• Data: Cloud SQL · Memorystore · Cloud Storage · Secret Manager
• Analytics: BigQuery -> Looker Studio / Power BI
• Ops: Monitoring, Logging, backups, multi-tenant isolation
Internet | Cloud LB / Caddy | +-- Chatwoot (GKE) --> Cloud SQL +-- agent (Run) --> Vertex AI (Gemini) +-- backend (Run) --> Vertex Search / | pgvector +-- Sidekiq/Redis (Memorystore) Secret Manager · Cloud Storage BigQuery --> Looker / Power BI Cloud Monitoring & Logging · Backups

## Slide 8: Data Migration: Zendesk to Platform
What we migrate:
  Tickets / conversations — historical records + status/labels -> Chatwoot conversations
  Contacts / customers — identities, phone/email, custom fields -> Chatwoot contacts
  Knowledge / Guide (FAQ) -> PROTON's owned KB (Vertex Search + pgvector)
  Attachments -> Cloud Storage · Reporting history -> BigQuery (trend continuity)
How — de-risked, no big-bang:
  Zendesk API export -> transform -> bulk import via Chatwoot API + KB ingest
  Parallel run: platform live alongside Zendesk during validation
  Cutover channel endpoints once validated, then decommission Zendesk after sign-off

## Slide 9
SECTION 3
Delivery
Project timeline, scope of work, out-of-scope boundaries and deliverables.

## Slide 10: Project Timeline (~12-16 weeks, phased)
Phase | Weeks | Focus | Key outcomes
P0 Discovery & GCP foundation | 1-2 | Access, data contracts, landing zone | GCP project, network, Secret Manager, CI; Zendesk export validated
P1 Core platform cutover | 3-7 | Stand up stack, migrate, wire channels | Chatwoot+agent+backend live; channels connected; KB migrated; AI+SOP live
P2 Gap closure | 6-12 | Genuine net-new work | Customer 360 + DMS/TSP; RBAC; telephony/IVR; Reports Tier-2
P3 Hardening & handover | 12-16 | HA, UAT, cutover | Autoscaling/HA, backups, monitoring; UAT sign-off; Zendesk decommissioned; training
Front half is largely assembly of already-built components; effort concentrates in P2's external-dependency items (DMS/TSP, telephony).

## Slide 11: Scope of Work
GCP landing zone: project, networking, IAM, Secret Manager, CI/CD
Production Chatwoot + agent + backend on GKE / Cloud Run + Cloud SQL
Omnichannel: WhatsApp, Email, Social (FB/IG), Web, Voice-to-text
AI layer: Gemini reply drafting, same-language answers, KB grounding, auto-classification
Knowledge base: migration + operator no-code authoring (FAQ + pgvector uploads)
Agent management: presence, priority routing, status-aware assignment, My-Tasks timers
Escalation & SLA: category->PIC, email+WhatsApp alerts, case states, auto-escalation, per-channel ACK
Lifecycle/SOP: disclaimers, idle-close, YES/NO gate, rating surveys, auto-categorization, email auto-ack
Customer 360 (DMS+TSP), RBAC roles, Reporting/BI, Zendesk data migration, ops & training

## Slide 12: Out of Scope
Telephony/PSTN carrier procurement — we integrate the CTI; the line contract is PROTON's (voice-to-text engine is built)
DMS / TSP source-system changes — we consume their APIs; internal changes are their owners'
SSI dealer-satisfaction survey workflow — lives in the e.MAS app; platform ingests & reports results only
Power BI licences — we connect to BigQuery; Microsoft licensing is PROTON's
Non-CRM business applications, custom hardware, end-user device management
Ongoing FAQ/KB content authoring after handover — enabled via no-code tools, owned by PROTON
Third-party SaaS subscriptions beyond the GCP + open-source stack

## Slide 13: Deliverables
Deliverable | Description
Production GCP environment | IaC-described GCP project running the platform
Migrated CRM | Chatwoot with imported Zendesk tickets, contacts, KB, attachments
AI automation layer | Gemini reply, classification, KB-grounded answers, SOP flows — live
Customer 360 integration | DMS/TSP two-way sync + 360 view card (pending PROTON API access)
RBAC | Roles & permissions model with admin UI
Reporting suite | BigQuery + Looker/Power BI, scheduled exports, anomaly alerts
Data-migration report | Record counts, fidelity validation, parallel-run results
Operations runbook + training | Deploy/backup/monitoring/provisioning + admin & agent sessions
UAT sign-off & cutover | Validated go-live and Zendesk decommission

## Slide 14: Why This Works
Proven — the platform already runs live against PROTON's SOP; this is migration + hardening, not invention.
Open & owned — no per-seat lock-in; PROTON controls the data, the AI, and the roadmap.
AI-native on Google — Gemini + Vertex AI, grounded on your own knowledge; measurable deflection and faster resolution.
Cost-down, capability-up — replace recurring SaaS licensing with managed infrastructure you scale on your terms.