## GCP Cost Estimation
16500
PROTON CRM — Monthly Recurring (one production tenant)
| No | GCP Component | Component Details | Price (USD) | Price (IDR)
| 1 | Google Kubernetes Engine (Standard) — cluster | Region: Singapore (asia-southeast1) Regional cluster management fee ($0.10/cluster/hr) Multi-tenant: per-tenant namespaces + node pools | 73
| 2 | Google Kubernetes Engine (Standard) — node pool | 3 × e2-standard-4 (vCPUs: 4, RAM: 16 GiB), on-demand Runs Chatwoot (Rails+Sidekiq), agent & backend (FastAPI) | 362.01
| 3 | Cloud SQL for PostgreSQL (HA) | Region: Singapore (asia-southeast1) Enterprise edition, regional HA Machine: 2 vCPU / 8 GiB RAM Storage: 100 GB SSD Chatwoot DB + per-tenant pgvector KB | 300
| 4 | Memorystore for Redis (HA) | Standard tier (auto-failover replica) Capacity: 4 GB Sidekiq queues / cache | 181.04
| 5 | Vertex AI — Gemini 2.5 Flash + Vertex AI Search | Usage-based (indicative) ~5,000 AI conversations/mo (~8k in + ~1.5k out tokens) ~5,000 grounded KB queries/mo | 50.75
| 6 | Cloud Storage | Region: Singapore (asia-southeast1) Class: Standard · 100 GB + modest egress Attachments / exports | 8.3
| 7 | Networking — Cloud Load Balancing + egress | 1 external HTTP(S) forwarding rule + data processing ~100 GB internet egress/mo | 31.85
| 8 | Cloud Logging + Cloud Monitoring | ~100 GB log ingest/mo (first 50 GB free) Metrics + alerting | 25
| 9 | Secret Manager + Artifact Registry + Cloud Build + BigQuery | Secrets · container images · CI builds · analytics warehouse (storage + query) | 17.25
Total Price Estimation Per-Month
Total Price Estimation Per-Year
Calculator Link: https://cloud.google.com/products/calculator
One-time — Migration Period *
| No | GCP Component | Component Details | Price (USD) | Price (IDR)
| 1 | Cloud Storage — migration staging | Zendesk export staging bucket (Standard, ~50 GB, short-lived) | 5
| 2 | Data transfer / egress — migration | One-time import/export bandwidth for tickets, contacts, KB, attachments | 15
| 3 | Temporary migration compute | Short-lived job for bulk import + KB ingest into Vertex AI Search / pgvector | 20
Total Price Estimation Per-Month
Total Price Estimation Per-Year
Calculator Link: https://cloud.google.com/products/calculator
*one time only during migration process
IDR shown at USD→IDR = cell A1 (16,500, editable). Indicative GCP list price (Jul 2026, asia-southeast1 / Singapore — nearest full-service region; Malaysia region not yet GA). Excludes negotiated discounts, taxes & Google program funding. 1-yr committed-use discount lowers nodes ~$233 → ~$920/mo total. Infrastructure is unchanged from the baseline workbook — it carries the whole platform, so it is not split between this scope and the Packages A-G scope.

## Timeline
Phases |  | Task | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8
Assessment & Planning
1.0 | 1.1 | Kick-off workshop; confirm scope against the BRD + Process-Flow workbook
| 1.2 | Validate the 5-channel complaint SOP and the escalation matrix
| 1.3 | Solution architecture, GCP landing-zone design & migration plan
GCP Foundation & Provisioning
2.0 | 2.1 | Provision GCP project, VPC, IAM & landing zone from accelerator IaC
| 2.2 | GKE Standard cluster + node pools; Cloud SQL (HA), Memorystore, BigQuery, Artifact Registry
| 2.3 | CI/CD (Cloud Build), Secret Manager, monitoring baseline & environment smoke test
Core Platform Cutover
3.0 | 3.1 | Deploy Chatwoot + agent + backend on GKE via accelerator Helm charts
| 3.2 | Migrate Zendesk tickets, contacts, history & attachments
| 3.3 | Migrate the knowledge base to pgvector + Vertex AI Search
| 3.4 | Wire channels: WhatsApp (Twilio), Website widget, API, Email
| 3.5 | Enable the AI layer & SOP lifecycle flows; reconcile migrated records
Gap Closure
4.0 | 4.1 | Email escalation — auto-ack once per thread + separate internal case
| 4.2 | Customer 360 card and the DMS/TSP integration surface
| 4.3 | Case management — hierarchical categories, per-case dashboard, RBAC
| 4.4 | Reporting & BI; agent management; bulk FAQ upload, multi-language & multimodal
Hardening, HA & UAT
5.0 | 5.1 | HA / autoscaling, resource tuning; monitoring, alerting & logging
| 5.2 | Backups & disaster-recovery runbook, with a restore test
| 5.3 | Security review, RBAC verification & secret rotation
| 5.4 | Live channel verification (WhatsApp, phone, email, web)
| 5.5 | UAT cycles, defect triage & fixes; data reconciliation & sign-off
Cutover, Handover & Training
6.0 | 6.1 | Cutover plan, go-live & hypercare window
| 6.2 | Zendesk decommission & licence termination
| 6.3 | Ops runbook; admin & agent training; knowledge transfer & closure
Accelerated delivery — 8 weeks (2 months), 36 working days of duration, against 16 weeks on the standard-build plan. The compression comes from the accelerator: the landing zone and GKE/Helm deployment are parameterised rather than authored, migration runs on existing tooling, HA/observability/DR ship as baselines, and the runbook and training material start from templates. Phases overlap — Gap Closure begins while the platform cutover is still settling. Assumes PROTON supplies the Zendesk export, DMS/TSP API access and UAT participants on schedule.

## PS Utilization
16500
[14 empty] | Role / Seniority | Sales price / hour (IDR) | Per day (× 8)
| Professional Services — PROTON CRM (self-managed on Google Cloud) · accelerated delivery, 2 months | [5 empty] | Lead Consultant | Lead Consultant | Senior Consultant | Consultant | Senior Consultant | Consultant | Total | Consultant | 350000
| Milestone | Activity | Resources | Duration (Week) | Service Price | Duration (Days) | Project Manager | Solution Architect / Tech Lead | Backend / AI Engineer | Frontend Engineer | Data / BI Engineer | QA Engineer | (mandays) | Senior Consultant | 606250
| Phase 1 : Assessment & Planning | • Kick-off workshop; confirm scope against the BRD + Process-Flow workbook • Validate the 5-channel complaint SOP and the escalation matrix • Solution architecture & GCP landing-zone design (GKE Standard, VPC, IAM) • Migration plan and Zendesk data-mapping approach • Delivery plan, RAID log and acceptance criteria agreed | Project Manager Solution Architect Backend/AI Engineer |  |  | 3 | 2 | 3 | 3 | 0 | 0 | 0 |  | Lead Consultant | 700000
| Phase 2 : GCP Foundation & Provisioning | • Provision GCP project, VPC, IAM and landing zone from accelerator IaC • Stand up GKE Standard cluster + node pools • Provision Cloud SQL (HA), Memorystore, BigQuery and Artifact Registry • Configure CI/CD (Cloud Build), Secret Manager and the monitoring baseline • Environment smoke test and access handover | Solution Architect DevOps / Backend Data/BI Engineer Project Manager |  |  | 3 | 2 | 3 | 3 | 1 | 2 | 1 |  | Principal | 825000
| Phase 3 : Core Platform Cutover | • Deploy Chatwoot + agent + backend on GKE via accelerator Helm charts • Migrate Zendesk tickets, contacts, history and attachments • Migrate the knowledge base to pgvector + Vertex AI Search • Wire channels: WhatsApp (Twilio), Website widget, API, Email • Enable the AI layer and SOP lifecycle flows (disclaimer, idle-close, YES/NO, rating, auto-classify) • Reconcile migrated records and confirm counts | Project Manager Backend/AI Engineer Frontend Engineer Data/BI Engineer QA |  |  | 10 | 5 | 1 | 10 | 10 | 2 | 2 |  | Expert / Director | 1275000
| Phase 4 : Gap Closure | • Email escalation — auto-ack once per thread + separate internal case • Customer 360 card and the DMS/TSP integration surface • Case management — hierarchical categories, per-case dashboard, RBAC • Reporting & BI — BigQuery views, role-based dashboards, NPS/CRR • Agent management — channel priority, auto-busy, status labels • Bulk FAQ/PDF upload; multi-language and multimodal handling | Backend/AI Engineer Frontend Engineer Data/BI Engineer Solution Architect QA |  |  | 5 | 5 | 3 | 5 | 5 | 2 | 2 |  | Margin | 15%
| Phase 5 : Hardening, HA & UAT | • HA / autoscaling and resource tuning • Monitoring, alerting and centralised logging • Backups and disaster-recovery runbook, with a restore test • Security review, RBAC verification and secret rotation • Live channel verification (WhatsApp, phone, email, web) • UAT cycles, defect triage and fixes; data reconciliation and sign-off | DevOps / Backend QA Backend/AI Engineer Data/BI Engineer Project Manager |  |  | 10 | 5 | 2 | 10 | 5 | 5 | 5
| Phase 6 : Cutover, Handover & Training | • Cutover plan, go-live and the hypercare window • Zendesk decommission and licence termination • Ops runbook — deploy, backup/restore, monitoring, tenant provisioning • Admin and agent training sessions • Knowledge transfer and project closure report | Project Manager Solution Architect Backend/AI Engineer Data/BI Engineer |  |  | 5 | 4 | 5 | 5 | 0 | 2 | 0
Total Mandays
Total Mandays Price
Total Price Including Margin
Accelerated delivery: 120 mandays over 36 working days (~2 months), against 252 mandays over 16 weeks on the standard-build plan. The compression comes from the accelerator — the landing zone and GKE/Helm deployment are parameterised rather than authored, migration runs on existing tooling, HA/observability/DR ship as baselines, release is scripted, and the runbook and training material start from templates. Assumes PROTON supplies the Zendesk export, DMS/TSP API access and UAT participants on schedule; slippage on any of those moves the go-live date rather than being absorbed. Mandays are an indicative delivery estimate; day-rates and margin are editable in the rate card (Q:S). Note the Solution Architect is priced at the Lead Consultant rate. May be offset by Google program funding.