## GCP Cost Estimation
16500
PROTON CRM — Monthly Recurring (one production tenant)
| No | GCP Component | Component Details | Price (USD) | Price (IDR)
| 1 | Google Kubernetes Engine (Standard) — cluster | Region: Singapore (asia-southeast1) Regional cluster management fee ($0.10/cluster/hr) Multi-tenant: per-tenant namespaces + node pools | 73
| 2 | Google Kubernetes Engine (Standard) — node pool | 3 × e2-standard-4 (vCPUs: 4, RAM: 16 GiB), on-demand Runs Chatwoot (Rails+Sidekiq), agent & backend (FastAPI) | 362.01
| 3 | Cloud SQL for PostgreSQL (HA) | Region: Singapore (asia-southeast1) Enterprise edition, regional HA Machine: 2 vCPU / 8 GiB RAM Storage: 100 GB SSD Chatwoot DB + per-tenant pgvector KB | 300
| 4 | Memorystore for Redis (HA) | Standard tier (auto-failover replica) Capacity: 4 GB Sidekiq queues / cache | 181.04
| 5 | Vertex AI — Gemini 2.5 Flash + Vertex AI Search | Usage-based (indicative) ~5,000 AI conversations/mo (~8k in + ~1.5k out tokens) ~5,000 grounded KB queries/mo | 50.75
| 6 | Cloud Storage | Region: Singapore (asia-southeast1) Class: Standard · 100 GB + modest egress Attachments / exports | 8.3
| 7 | Networking — Cloud Load Balancing + egress | 1 external HTTP(S) forwarding rule + data processing ~100 GB internet egress/mo | 31.85
| 8 | Cloud Logging + Cloud Monitoring | ~100 GB log ingest/mo (first 50 GB free) Metrics + alerting | 25
| 9 | Secret Manager + Artifact Registry + Cloud Build + BigQuery | Secrets · container images · CI builds · analytics warehouse (storage + query) | 17.25
Total Price Estimation Per-Month
Total Price Estimation Per-Year
Calculator Link: https://cloud.google.com/products/calculator
One-time — Migration Period *
| No | GCP Component | Component Details | Price (USD) | Price (IDR)
| 1 | Cloud Storage — migration staging | Zendesk export staging bucket (Standard, ~50 GB, short-lived) | 5
| 2 | Data transfer / egress — migration | One-time import/export bandwidth for tickets, contacts, KB, attachments | 15
| 3 | Temporary migration compute | Short-lived job for bulk import + KB ingest into Vertex AI Search / pgvector | 20
Total Price Estimation Per-Month
Total Price Estimation Per-Year
Calculator Link: https://cloud.google.com/products/calculator
*one time only during migration process
IDR shown at USD→IDR = cell A1 (16,500, editable). Indicative GCP list price (Jul 2026, asia-southeast1 / Singapore — nearest full-service region; Malaysia region not yet GA). Excludes negotiated discounts, taxes & Google program funding. 1-yr committed-use discount lowers nodes ~$233 → ~$920/mo total. Infrastructure is unchanged from the baseline workbook — it carries the whole platform, so it is not split between this scope and the Packages A-G scope.

## Timeline
Phases |  | Task | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14
GCP Foundation & Provisioning
1.0 | 1.1 | Provision GCP project, VPC, IAM, GKE Standard cluster + node pools
| 1.2 | Cloud SQL, Memorystore, BigQuery, Artifact Registry; CI/CD, Secret Manager, monitoring baseline
| 1.3 | Re-platform Chatwoot + agent + backend from Docker Compose to GKE manifests
Data Migration & Channel Cutover
2.0 | 2.1 | Zendesk extract, field mapping & bulk import (tickets, contacts, attachments)
| 2.2 | KB migration to pgvector + Vertex AI Search corpus
| 2.3 | Re-wire WhatsApp (Twilio), Website, API & Email inboxes on the new cluster
| 2.4 | Parallel-run (Zendesk + new CRM) & data reconciliation
Platform Features outside Packages A–G
3.0 | 3.1 | Native SAML SSO — IdP metadata, ACS endpoint, JIT provisioning, Security settings UI
| 3.2 | RBAC phase 3 — native conversation-visibility scoping
| 3.3 | IVR-4 — voice-language reliability diagnosis & fix
| 3.4 | Custom agent status labels (Follow-up / Lunch / Break) + routing integration
| 3.5 | Release & enablement — Chatwoot image rebuild (patches 0034–0041), RSA DB provisioning, BigQuery view rollout, per-tenant flags
Hardening, HA & UAT
4.0 | 4.1 | HA / autoscaling, resource tuning, monitoring & alerting
| 4.2 | Backups & disaster-recovery runbook
| 4.3 | Live channel verification (real WhatsApp, phone call, browser smoke)
| 4.4 | UAT, data reconciliation & sign-off
Cutover, Decommission & Handover
5.0 | 5.1 | Go-live cutover & hypercare
| 5.2 | Zendesk decommission
| 5.3 | Ops runbook + admin/agent training & knowledge transfer
Memo — priced separately
— | A–G | Packages A–G (email/social, Contacts 360 merge, telephony, demo data & case detail, reporting deck parity, DMS/TSP, escalation-policy engine) — already queued, own estimate
Timeline covers the scope outside Packages A–G only. Phase durations overlap — the sum of phase weeks exceeds the 14-week calendar because Phase 3 runs alongside Phases 1–2.

## PS Utilization
16500
[17 empty] | Role / Seniority | Sales price / hour (IDR) | Per day (× 8)
| Professional Services — PROTON CRM · scope outside Packages A–G | [5 empty] | Lead Consultant | Principal | Senior Consultant | Consultant | Senior Consultant | Consultant | Total | Risk buffer |  |  | Consultant | 350000
| Milestone | Activity | Resources | Duration (Week) | Service Price | Duration (Days) | Project Manager | Solution Architect / Tech Lead | Backend / AI Engineer | Frontend Engineer | Data / BI Engineer | QA Engineer | (mandays) | Risk % | Contingency (mandays) | Total incl. contingency | Senior Consultant | 606250
| Phase 1 : GCP Foundation & Provisioning | Provision GCP project, VPC, IAM, GKE Standard cluster + node pools, Cloud SQL, Memorystore, BigQuery, Artifact Registry; CI/CD, Secret Manager, monitoring baseline; re-platform Chatwoot + agent + backend from Docker Compose to GKE manifests. | Solution Architect DevOps / Backend Data/BI Engineer Project Manager | 3 |  |  | 3 | 10 | 12 | 0 | 3 | 2 |  | 10% |  |  | Lead Consultant | 700000
| Phase 2 : Data Migration & Channel Cutover | Zendesk extract, field mapping & bulk import (tickets, contacts, attachments); KB migration to pgvector + Vertex AI Search; re-wire WhatsApp/Website/API/Email inboxes on the new cluster; parallel-run & reconciliation. | Backend/AI Engineer Data/BI Engineer Frontend Engineer QA Project Manager | 4 |  |  | 4 | 4 | 16 | 4 | 6 | 6 |  | 20% |  |  | Principal | 825000
| Phase 3 : Platform Features outside Packages A–G | Native SAML SSO (IdP metadata, ACS endpoint, JIT provisioning, Security settings UI); RBAC phase 3 — native conversation-visibility scoping; IVR-4 voice-language reliability fix; custom agent status labels + routing integration; release & enablement (Chatwoot image rebuild with patches 0034–0041, RSA DB provisioning, BigQuery view rollout, per-tenant feature flags). | Backend/AI Engineer Frontend Engineer Solution Architect QA Data/BI Engineer | 8 |  |  | 3 | 9 | 33 | 13 | 3 | 15 |  | 20% |  |  | Expert / Director | 1275000
| Phase 4 : Hardening, HA & UAT | HA / autoscaling & resource tuning; monitoring, alerting & logging; backups and disaster-recovery runbook; live channel verification (real WhatsApp, phone call, browser smoke); UAT, data reconciliation & sign-off. | DevOps / Backend QA Solution Architect Project Manager | 4 |  |  | 6 | 5 | 11 | 3 | 2 | 20 |  | 10% |  |  | Margin | 15%
| Phase 5 : Cutover, Decommission & Handover | Go-live cutover & hypercare; Zendesk decommission; ops runbook + admin/agent training & knowledge transfer. | Project Manager Backend/AI Engineer DevOps Technical Writer | 2 |  |  | 6 | 3 | 5 | 2 | 2 | 3 |  | 5%
Total Mandays
Total Mandays Price
Contingency (risk buffer)
Subtotal incl. Contingency
Total Price Including Margin
Memo — excluded from the totals above (priced separately)
| Packages A–G (in delivery) | A· Facebook/Instagram activation · B· Contacts ↔ Customer 360 merge · C· Telephony (live handoff, transcript-to-ticket, auto-busy, call recording) · D· Demo data & per-case detail · E· Reporting parity with the weekly/monthly decks · F· DMS/TSP integration · G· Escalation-policy engine. | Already queued — separate estimate |  | —
Scope is zero-based on the work outside Packages A–G: platform delivery that has not started (GCP landing zone, GKE re-platform, Zendesk + KB migration, cutover, UAT, handover) plus the product items that have a spec/plan but no code (native SAML SSO, RBAC phase 3, IVR-4, custom agent status labels, release/enablement and live verification). Mandays are an indicative delivery estimate; day-rates, margin and per-phase Risk % are editable (rate card in T:V, Risk % in column P). May be offset by Google program funding.